## Sheet1
Capstone Hours |  |  |  |  | Goal: 2+ hours weekdays 5+ hours weekends
|  |  | Calculated: | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | I didn't even mean to make up for my missed hours haha | [5 empty] | Week 6 | [6 empty] | Week 7 | I think the project should go gold this week | [5 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
Date: | Start Time: | End Time: | Duration: | Running Total: | What I accomplished: | What do I think I should do next session: |  | Date: | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08
2023-10-02 | 11:00 | 12:40 | 1:40 | 1 hours 40 minutes |  |  |  | Total Time: | 01 hours 40 minutes | 02 hours 53 minutes | 02 hours 20 minutes | 02 hours 56 minutes | 03 hours 52 minutes | 06 hours 28 minutes | 02 hours 38 minutes | 03 hours 33 minutes | 05 hours 50 minutes | 04 hours 23 minutes | 03 hours 35 minutes | 04 hours 35 minutes | 07 hours 00 minutes | 03 hours 25 minutes | 03 hours 50 minutes | 04 hours 10 minutes | 02 hours 40 minutes | 02 hours 21 minutes | 03 hours 30 minutes | 05 hours 07 minutes | 02 hours 25 minutes | 00 hours 00 minutes | 04 hours 17 minutes | 02 hours 08 minutes | 02 hours 25 minutes | 04 hours 20 minutes | 05 hours 05 minutes | 04 hours 05 minutes | 00 hours 00 minutes | 06 hours 11 minutes | 02 hours 15 minutes | 01 hours 55 minutes | 05 hours 45 minutes | 00 hours 10 minutes | 00 hours 00 minutes | 02 hours 07 minutes | 02 hours 00 minutes | 02 hours 40 minutes | 02 hours 25 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes
2023-10-03 | 17:00 | 19:53 | 2:53 | 4 hours 33 minutes | Spent a lot of time wrestling with my PC, Had to reinstall WSL. I also got more progress on the "generate component" function. All of that progress is untested. |  |  | Goal Time: | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 5 hours | 5 hours | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 5 hours | 5 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours
2023-10-04 | 9:50 | 12:10 | 2:20 | 6 hours 53 minutes | Got component generation working!! I need to work on the system prompt, as well as renaming "effects" to "side effects" or "useEffect methods" or something like that. |  |  | Running Total: | 1 hours 40 minutes | 4 hours 33 minutes | 6 hours 53 minutes | 9 hours 49 minutes | 13 hours 41 minutes | 20 hours 9 minutes | 22 hours 47 minutes | 26 hours 20 minutes | 32 hours 9.99999999999977 minutes | 36 hours 33 minutes | 40 hours 8 minutes | 44 hours 43 minutes | 51 hours 43 minutes | 55 hours 8 minutes | 58 hours 58 minutes | 63 hours 8 minutes | 65 hours 48 minutes | 68 hours 9.00000000000045 minutes | 71 hours 39 minutes | 76 hours 46 minutes | 79 hours 11 minutes | 79 hours 11 minutes | 83 hours 28 minutes | 85 hours 36 minutes | 88 hours 1 minutes | 92 hours 21 minutes | 97 hours 26 minutes | 101 hours 31 minutes | 101 hours 31 minutes | 107 hours 42 minutes | 109 hours 57 minutes | 111 hours 52 minutes | 117 hours 37 minutes | 117 hours 47 minutes | 117 hours 47 minutes | 119 hours 54 minutes | 121 hours 54 minutes | 124 hours 34 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes | 126 hours 59 minutes
2023-10-05 | 9:30 | 12:26 | 2:56 | 9 hours 49 minutes | Got some frontend work done. I started a gridpane component for the editor. | Make dragging the dividers change the size of the columns | done | Running Goal: | 2 hours | 4 hours | 6 hours | 8 hours | 10 hours | 15 hours | 20 hours | 22 hours | 24 hours | 26 hours | 28 hours | 30 hours | 35 hours | 40 hours | 42 hours | 46 hours | 48 hours | 50 hours | 53 hours | 58 hours | 60 hours | 62 hours | 66 hours | 68 hours | 70 hours | 73 hours | 78 hours | 80 hours | 82 hours | 86 hours | 88 hours | 90 hours | 93 hours | 98 hours | 100 hours | 102 hours | 106 hours | 108 hours | 110 hours | 113 hours | 118 hours | 120 hours
2023-10-06 | 12:43 | 16:35 | 3:52 | 13 hours 41 minutes | Got a lot of work on the GridPane component. | Refactor the ConversationWindow to have its state managed by the page. Also refactor it to have a toggle between 3.5 and 4. | done
2023-10-07 | 14:07 | 18:30 | 4:23 | 18 hours 4 minutes | Got themes set up, added GPT switch to conversation window, added styles accordingly, got a landing page and sign in/up started | Get conversation window talking to the backend. More work on the editor page | done
2023-10-07 | 19:15 | 21:20 | 2:05 | 20 hours 9 minutes | Made progress towards chat component being tied to GPT | I didn't get the ConversationWindow tied to GPT yet. Do that | done
2023-10-08 | 11:15 | 12:40 | 1:25 | 21 hours 34 minutes | Frontend conversationWindow hits GPT! Also the TextField is multiline now | I need to start work on the syntax code display. I don't want code to be shown the same as regular messages. Fix the fact that multiline messages don't actually appear multiline in messages | done
2023-10-08 | 20:15 | 21:28 | 1:13 | 22 hours 47 minutes | Got code snippets working in gpt messages | Next frontend task is the text editor. It's time to start slate stuff. Generally lots of frontend stuff needs doing. Maybe mock out layouts. | done
2023-10-09 | 14:40 | 15:05 | 0:25 | 23 hours 12 minutes | Researching Web Containers and editors | https://www.npmjs.com/package/@monaco-editor/react | done
2023-10-09 | 17:12 | 20:20 | 3:08 | 2 hours 20 minutes | Styled Monaco and researched a react preview solution. Pondered an easier solution than web containers, but I've decided against that for a better capstone | Setup Web containers: https://stackblitz.com/edit/stackblitz-webcontainer-api-starter-1ceghg?file=files.js https://webcontainers.io/tutorial/1-build-your-first-webcontainer-app | done
2023-10-10 | 10:15 | 13:30 | 3:15 | 5 hours 35 minutes | Web containers work as a proof of conept! | Now is the heavy meat and potatoes of getting project file structure going. The startup process for a web container is going to be copying all the files over, installing the dependencies, then starting the server. (we are not using npx create-react-app) | done
2023-10-10 | 16:50 | 19:25 | 2:35 | 8 hours 10 minutes | Made tab bars for editor and snippet, polished other bits of code |  |  | It's weird to think this is a shared document. Not through excel, but github lol
2023-10-11 | 10:05 | 12:20 | 2:15 | 10 hours 25 minutes | Refactored the view panels to not be bad. Now the editor development can really start. I also sketched out what the pages might look like
2023-10-11 | 18:37 | 20:45 | 2:08 | 12 hours 33 minutes | Finished up the view panels, started on the sidebar, started laying out the editor page | Next items on the horizon are: file heirarchy viewer, theme switcher, settings, terminal, top bar, moving most state into a context, as well as starting on a lot of backend type shit | Need to do backend stuff
2023-10-12 | 11:20 | 13:10 | 1:50 | 14 hours 23 minutes | Moved a lot of state to an editor context (I think all?), I also made a loading display for the react preview, and I moved the editor to /editor instead of /demo | Next is changing the react preview to mount a basic create-react-app file template instead of npm i. Along with that I should figure out how to use pnpm instead of npm | done
2023-10-12 | 17:30 | 19:15 | 1:45 | 16 hours 8 minutes | I got the web containers mounting a react template that is stored as json instead of using npx create-react-app. I don't know if it's faster, but it is more controllable. | Next task is the file heirarchy viewer/selector. First view, then select opens it on the code editor | done
2023-10-13 | 10:55 | 13:35 | 2:40 | 18 hours 48 minutes | Got live editing working instead of doing what I said I needed to do next! Also did some theme tweaking
2023-10-13 | 19:45 | 21:40 | 1:55 | 20 hours 43 minutes | Got a lot of progress done on the file viewer/selector | Next is making it actually open a file, also the terminal | done
2023-10-14 | 12:45 | 19:45 | 7:00 | 3 hours 43 minutes | Got the file explorer opening files! I also got it so files generated by npm i are shown to the user. Also you can select a specific file using tabs in the code editor | Next up is the terminal. Also I need to deal with technical debt soon if not now | done
2023-10-15 | 14:50 | 18:15 | 3:25 | 7 hours 8 minutes | Got the terminal working! It shows dependencies getting downloaded, then becomes available to the user! The fileviewer doesn't automatically update, but it does have a refresh button | Auto fileviewer refresh is on the horizon, but not something I want to immediately tackle. Next will be fixing technical debt | Need to do auto refresh
2023-10-16 | 19:20 | 23:10 | 3:50 | 10 hours 58 minutes | Refactored the state of the application to be less of a massive headache. Implemented custom hooks to grab select groups of values from the context. I also moved fragile code to a context. | I think the next thing on the quest to refactor is addressing all clouds/thought bubbles 💭 | Addressed many
2023-10-17 | 11:15 | 13:25 | 2:10 | 13 hours 8 minutes | Addressed many 💭 comments and general polish
2023-10-17 | 13:55 | 15:55 | 2:00 | 15 hours 8 minutes | So much polish, I seperated a bunch of inline styles into variables outside the return statement, I did the same thing with a bunch of inline methods as well. I also created a few stories. | I think the next big task is setting up the database to store projects and profiles, The next little thing is the "diff" button and more AI features. I think the plan is diff button, big DB stuff, then back to AI features like refactor |  | https://next-auth.js.org/configuration/providers/oauth
2023-10-18 | 15:35 | 18:15 | 2:40 | 17 hours 48 minutes | Got Oauth working on the frontend | Next session it's time to make the database side of accounts, this include credential sign ins and connecting Oauth accounts
2023-10-19 | 10:10 | 11:01 | 0:51 | 18 hours 39 minutes | Got backend auth started | Next is finishing backend auth
2023-10-19 | 13:00 | 13:30 | 0:30 | 19 hours 9 minutes | Got some dependencies installed, a pydantic account model made, and learned that my old JWT method is deprecated | Gotta continue setting up backend auth
2023-10-19 | 14:55 | 15:55 | 1:00 | 20 hours 9 minutes | More progress on backend account system. I'm getting fundamentals done and getting basic scaffolding/planning done | Keep going with backend Account system
2023-10-20 | 11:30 | 15:00 | 3:30 | 23 hours 39 minutes | Got authentication and session figured out between the backend and the frontend | Next step is getting OAuth accounts created in our backend, and merging accounts with the same email
2023-10-21 | 12:00 | 12:32 | 0:32 | 0 hours 11 minutes | Only taking a break to bathroom
2023-10-21 | 13:05 | 15:40 | 2:35 | 2 hours 46 minutes | Got a lot of project API made, added some to auth/account API | Next is adding projects to users, then getting the frontend "register -> login -> create project -> open project" flow
2023-10-21 | 17:05 | 19:05 | 2:00 | 4 hours 46 minutes | Got the register frontend wired to backend alongsied making the security code for the non auth apis, a new project endpoint, and some more account and project endpoints | Next is the dashboard/account page
2023-10-22 | 10:35 | 11:25 | 0:50 | 5 hours 36 minutes | Got started on dashboard, mostly only got design ideas started. I got stuck then the internet died | Make the dashboard page
2023-10-22 | 19:50 | 21:25 | 1:35 | 7 hours 11 minutes | The dashboard shows the logged in users projects. The editor page can now load from a user's saved project | Next is the "new project" button, as well as figuring out how to make the attrocious loading times a better experience
2023-10-24 | 16:05 | 20:22 | 4:17 | 11 hours 28 minutes | I got a lot of work done on the dashboard. The project list can now create projects | I want to add a template system, coming up soon will also be adding files and folders in the editor, as well as finally getting to the navbar
2023-10-25 | 17:30 | 19:38 | 2:08 | 13 hours 36 minutes | Implemented most if not all of the template backend | Next is template frontend stuff, I think I will start with the new template stuff to finish off the new project form, then jump to finishing up the editor. This is a nice transition since the editor needs a "Set as template" space
2023-10-26 | 16:15 | 18:40 | 2:25 | 16 hours 1 minutes | Started work on ProjectList, then got distracted trying to adjust for timezone. I failed. I also made some backend tweaks to data types, might do more
2023-10-27 | 16:00 | 20:20 | 4:20 | 20 hours 21 minutes | I fixed the timestamps, some datatypes, made a shared models folder so I can have the same models between my python APIs, and modified the loading component | Next I want to finish the auto sign out, after that I think I wanna do the editor navbar and other editor things
2023-10-28 | 12:50 | 16:05 | 3:15 | 23 hours 36 minutes | Started the topbar frontend bits, created a new context hook for project metadata, changed how redirects work, also fixed auto sign out I think | Next is navbar functionality, the profile component, more dashboard progress, making the settings sidebar panel, and redoing the terminal scrollbar | Not actually all of these, I'm just listing some options
2023-10-28 | 18:30 | 20:20 | 1:50 | 1 hours 26 minutes | messed with theme colors and project config frontend, fixed index button
2023-10-29 | 12:55 | 15:00 | 2:05 | 3 hours 31 minutes | Got the save button working, sonfig menu as well
2023-10-29 | 15:25 | 17:25 | 2:00 | 5 hours 31 minutes | Merged the SignIn/Up pages and made them look real nice, also refactored TopBar, then also fixed the part that I entirely broke | Index and dashboard need work. Editor still needs some crucial buttons and the auto file display update
2023-10-31 | 11:40 | 14:41 | 3:01 | 8 hours 32 minutes | Broke next.js hot reload, tweaked saving, starting on auto filestructure updating
2023-10-31 | 16:45 | 19:55 | 3:10 | 11 hours 42 minutes | Fixed the hot reload, got auto filestructuredisplay updating, started with the add file/folder button, fixed auto sign out, added some new fileOperations, fixed SharedArrayBuffer bug, improved saving and editor tabs | Next is the new file/folder button functionality
2023-11-01 | 18:55 | 21:10 | 2:15 | 13 hours 57 minutes | Styling and file/folder name validation | ^^^^^^^^^^^^
2023-11-02 | 18:10 | 20:05 | 1:55 | 15 hours 52 minutes | New file/folder feature complete, sign in page buttons are Oauth again, the editor no longer requires you to be signed in to open a project, but you must be an owner or collaborator to save, save icon expands when project not saved | Next is the fork feature, then finally the diff button? Also need to add rename nad delete files
2023-11-03 | 11:35 | 17:20 | 5:45 | 21 hours 37 minutes | Folder and File Renaming! | Delete Files, diff button, fork button, profile viewer/search
2023-11-04 | 15:50 | 16:00 | 0:10 | 21 hours 47 minutes | Delete folders and files woohoo!
2023-11-06 | 17:17 | 19:24 | 2:07 | 23 hours 54 minutes | Reworked dashboard looks, added the profile view to it. Also made but didn not test the search for user endpoint, and made the get projects endpoints sort by last modified date | Next is making the profile viewer/editor actually update the profile, and add the profile collaborator components to the editor
2023-11-07 | 15:40 | 17:40 | 2:00 | 1 hours 54 minutes | Made the profile component on the dashboard update profiles, added profile accordions to the project config in the editor | Next is making the add and remove collaborator functions, right now the component is just pretty frontend | Need to make a public account view
2023-11-08 | 17:50 | 20:30 | 2:40 | 4 hours 34 minutes | I got the collaborator stuff working! Collaborators can see shared projects on their dashboard, as well as update projects shared with them! Oh also custom scrollbars in some places | I don't know what in particular to do next, but I know the diff button needs work still lol
2023-11-09 | 17:05 | 19:30 | 2:25 | 6 hours 59 minutes | Diff button finally implemented!!!! Mini File Display for the template preview on create project is implemented!! Started reworking the landing page! | Next is the public profile page/endpoints, as well as finishing up the landing page