## Sheet1
Capstone Hours |  |  |  |  | Goal: 2+ hours weekdays 5+ hours weekends
Calculated:
Date: | Start Time: | End Time: | Duration: | Running Total: | What I accomplished: | What do I think I should do next session: | Date: | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08
2023-10-02 | 11:00 | 12:40 | 1:40 | 1 hours 40 minutes |  |  | Total Time: | 01 hours 40 minutes | 02 hours 53 minutes | 02 hours 20 minutes | 02 hours 56 minutes | 03 hours 52 minutes | 06 hours 28 minutes | 01 hours 25 minutes
2023-10-03 | 17:00 | 19:53 | 2:53 | 4 hours 33 minutes | Spent a lot of time wrestling with my PC, Had to reinstall WSL. I also got more progress on the "generate component" function. All of that progress is untested. |  | Distance From Goal Time: | 0 hours 20 minutes | Goal Met! | Goal Met! | Goal Met! | Goal Met! | Goal Met! | 4 hours 35 minutes
2023-10-04 | 9:50 | 12:10 | 2:20 | 6 hours 53 minutes | Got component generation working!! I need to work on the system prompt, as well as renaming "effects" to "side effects" or "useEffect methods" or something like that. |  | Goal Time: | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 5 hours | 5 hours
2023-10-05 | 9:30 | 12:26 | 2:56 | 9 hours 49 minutes | Got some frontend work done. I started a gridpane component for the editor. | Make dragging the dividers change the size of the columns | Running Total: | 1 hours 40 minutes | 4 hours 33 minutes | 6 hours 53 minutes | 9 hours 49 minutes | 13 hours 41 minutes | 20 hours 9 minutes | 21 hours 34 minutes
2023-10-06 | 12:43 | 16:35 | 3:52 | 13 hours 41 minutes | Got a lot of work on the GridPane component. | Refactor the ConversationWindow to have its state managed by the page. Also refactor it to have a toggle between 3.5 and 4. | Running Goal: | 2 hours | 4 hours | 6 hours | 8 hours | 10 hours | 15 hours | 20 hours
2023-10-07 | 14:07 | 18:30 | 4:23 | 18 hours 4 minutes | Got themes set up, added GPT switch to conversation window, added styles accordingly, got a landing page and sign in/up started | Get conversation window talking to the backend. More work on the editor page | bar: 2023-10-02; 2023-10-07 to 2023-10-08
2023-10-07 | 19:15 | 21:20 | 2:05 | 20 hours 9 minutes | Made progress towards chat component being tied to GPT | I didn't get the ConversationWindow tied to GPT yet. Do that
2023-10-08 | 11:15 | 12:40 | 1:25 | 21 hours 34 minutes | Frontend conversationWindow hits GPT! Also the TextField is multiline now | I need to start work on the syntax code display. I don't want code to be shown the same as regular messages. Fix the fact that multiline messages don't actually appear multiline in messages
2023-10-08 | 20:15