## Sheet1
Capstone Hours |  |  |  |  | Goal: 2+ hours weekdays 5+ hours weekends
|  |  | Calculated: | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | I think the project should go gold this week | [5 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
Date: | Start Time: | End Time: | Duration: | Running Total: | What I accomplished: | What do I think I should do next session: |  | Date: | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08
2023-10-02 | 11:00 | 12:40 | 1:40 | 1 hours 40 minutes |  |  |  | Total Time: | 01 hours 40 minutes | 02 hours 53 minutes | 02 hours 20 minutes | 02 hours 56 minutes | 03 hours 52 minutes | 06 hours 28 minutes | 02 hours 38 minutes | 03 hours 33 minutes | 05 hours 50 minutes | 04 hours 23 minutes | 03 hours 35 minutes | 04 hours 35 minutes | 07 hours 00 minutes | 03 hours 25 minutes | 03 hours 50 minutes | 04 hours 10 minutes | 02 hours 40 minutes | 02 hours 21 minutes | 03 hours 30 minutes | 05 hours 07 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes | 00 hours 00 minutes
2023-10-03 | 17:00 | 19:53 | 2:53 | 4 hours 33 minutes | Spent a lot of time wrestling with my PC, Had to reinstall WSL. I also got more progress on the "generate component" function. All of that progress is untested. |  |  | Goal Time: | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 5 hours | 5 hours | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 5 hours | 5 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours | 5 hours | 2 hours | 2 hours | 4 hours | 2 hours | 2 hours | 3 hours
2023-10-04 | 9:50 | 12:10 | 2:20 | 6 hours 53 minutes | Got component generation working!! I need to work on the system prompt, as well as renaming "effects" to "side effects" or "useEffect methods" or something like that. |  |  | Running Total: | 1 hours 40 minutes | 4 hours 33 minutes | 6 hours 53 minutes | 9 hours 49 minutes | 13 hours 41 minutes | 20 hours 9 minutes | 22 hours 47 minutes | 26 hours 20 minutes | 32 hours 9.99999999999977 minutes | 36 hours 33 minutes | 40 hours 8 minutes | 44 hours 43 minutes | 51 hours 43 minutes | 55 hours 8 minutes | 58 hours 58 minutes | 63 hours 8 minutes | 65 hours 48 minutes | 68 hours 9.00000000000045 minutes | 71 hours 39 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes | 76 hours 46 minutes
2023-10-05 | 9:30 | 12:26 | 2:56 | 9 hours 49 minutes | Got some frontend work done. I started a gridpane component for the editor. | Make dragging the dividers change the size of the columns | done | Running Goal: | 2 hours | 4 hours | 6 hours | 8 hours | 10 hours | 15 hours | 20 hours | 22 hours | 24 hours | 26 hours | 28 hours | 30 hours | 35 hours | 40 hours | 42 hours | 46 hours | 48 hours | 50 hours | 53 hours | 58 hours | 60 hours | 62 hours | 66 hours | 68 hours | 70 hours | 73 hours | 78 hours | 80 hours
2023-10-06 | 12:43 | 16:35 | 3:52 | 13 hours 41 minutes | Got a lot of work on the GridPane component. | Refactor the ConversationWindow to have its state managed by the page. Also refactor it to have a toggle between 3.5 and 4. | done
2023-10-07 | 14:07 | 18:30 | 4:23 | 18 hours 4 minutes | Got themes set up, added GPT switch to conversation window, added styles accordingly, got a landing page and sign in/up started | Get conversation window talking to the backend. More work on the editor page | done
2023-10-07 | 19:15 | 21:20 | 2:05 | 20 hours 9 minutes | Made progress towards chat component being tied to GPT | I didn't get the ConversationWindow tied to GPT yet. Do that | done
2023-10-08 | 11:15 | 12:40 | 1:25 | 21 hours 34 minutes | Frontend conversationWindow hits GPT! Also the TextField is multiline now | I need to start work on the syntax code display. I don't want code to be shown the same as regular messages. Fix the fact that multiline messages don't actually appear multiline in messages | done
2023-10-08 | 20:15 | 21:28 | 1:13 | 22 hours 47 minutes | Got code snippets working in gpt messages | Next frontend task is the text editor. It's time to start slate stuff. Generally lots of frontend stuff needs doing. Maybe mock out layouts. | done
2023-10-09 | 14:40 | 15:05 | 0:25 | 23 hours 12 minutes | Researching Web Containers and editors | https://www.npmjs.com/package/@monaco-editor/react | done
2023-10-09 | 17:12 | 20:20 | 3:08 | 2 hours 20 minutes | Styled Monaco and researched a react preview solution. Pondered an easier solution than web containers, but I've decided against that for a better capstone | Setup Web containers: https://stackblitz.com/edit/stackblitz-webcontainer-api-starter-1ceghg?file=files.js https://webcontainers.io/tutorial/1-build-your-first-webcontainer-app | done
2023-10-10 | 10:15 | 13:30 | 3:15 | 5 hours 35 minutes | Web containers work as a proof of conept! | Now is the heavy meat and potatoes of getting project file structure going. The startup process for a web container is going to be copying all the files over, installing the dependencies, then starting the server. (we are not using npx create-react-app) | done
2023-10-10 | 16:50 | 19:25 | 2:35 | 8 hours 10 minutes | Made tab bars for editor and snippet, polished other bits of code |  |  | It's weird to think this is a shared document. Not through excel, but github lol
2023-10-11 | 10:05 | 12:20 | 2:15 | 10 hours 25 minutes | Refactored the view panels to not be bad. Now the editor development can really start. I also sketched out what the pages might look like
2023-10-11 | 18:37 | 20:45 | 2:08 | 12 hours 33 minutes | Finished up the view panels, started on the sidebar, started laying out the editor page | Next items on the horizon are: file heirarchy viewer, theme switcher, settings, terminal, top bar, moving most state into a context, as well as starting on a lot of backend type shit | Need to do backend stuff
2023-10-12 | 11:20 | 13:10 | 1:50 | 14 hours 23 minutes | Moved a lot of state to an editor context (I think all?), I also made a loading display for the react preview, and I moved the editor to /editor instead of /demo | Next is changing the react preview to mount a basic create-react-app file template instead of npm i. Along with that I should figure out how to use pnpm instead of npm | done
2023-10-12 | 17:30 | 19:15 | 1:45 | 16 hours 8 minutes | I got the web containers mounting a react template that is stored as json instead of using npx create-react-app. I don't know if it's faster, but it is more controllable. | Next task is the file heirarchy viewer/selector. First view, then select opens it on the code editor | done
2023-10-13 | 10:55 | 13:35 | 2:40 | 18 hours 48 minutes | Got live editing working instead of doing what I said I needed to do next! Also did some theme tweaking
2023-10-13 | 19:45 | 21:40 | 1:55 | 20 hours 43 minutes | Got a lot of progress done on the file viewer/selector | Next is making it actually open a file, also the terminal | done
2023-10-14 | 12:45 | 19:45 | 7:00 | 3 hours 43 minutes | Got the file explorer opening files! I also got it so files generated by npm i are shown to the user. Also you can select a specific file using tabs in the code editor | Next up is the terminal. Also I need to deal with technical debt soon if not now | done
2023-10-15 | 14:50 | 18:15 | 3:25 | 7 hours 8 minutes | Got the terminal working! It shows dependencies getting downloaded, then becomes available to the user! The fileviewer doesn't automatically update, but it does have a refresh button | Auto fileviewer refresh is on the horizon, but not something I want to immediately tackle. Next will be fixing technical debt | Need to do auto refresh
2023-10-16 | 19:20 | 23:10 | 3:50 | 10 hours 58 minutes | Refactored the state of the application to be less of a massive headache. Implemented custom hooks to grab select groups of values from the context. I also moved fragile code to a context. | I think the next thing on the quest to refactor is addressing all clouds/thought bubbles 💭 | Addressed many
2023-10-17 | 11:15 | 13:25 | 2:10 | 13 hours 8 minutes | Addressed many 💭 comments and general polish
2023-10-17 | 13:55 | 15:55 | 2:00 | 15 hours 8 minutes | So much polish, I seperated a bunch of inline styles into variables outside the return statement, I did the same thing with a bunch of inline methods as well. I also created a few stories. | I think the next big task is setting up the database to store projects and profiles, The next little thing is the "diff" button and more AI features. I think the plan is diff button, big DB stuff, then back to AI features like refactor |  | https://next-auth.js.org/configuration/providers/oauth
2023-10-18 | 15:35 | 18:15 | 2:40 | 17 hours 48 minutes | Got Oauth working on the frontend | Next session it's time to make the database side of accounts, this include credential sign ins and connecting Oauth accounts
2023-10-19 | 10:10 | 11:01 | 0:51 | 18 hours 39 minutes | Got backend auth started | Next is finishing backend auth
2023-10-19 | 13:00 | 13:30 | 0:30 | 19 hours 9 minutes | Got some dependencies installed, a pydantic account model made, and learned that my old JWT method is deprecated | Gotta continue setting up backend auth
2023-10-19 | 14:55 | 15:55 | 1:00 | 20 hours 9 minutes | More progress on backend account system. I'm getting fundamentals done and getting basic scaffolding/planning done | Keep going with backend Account system
2023-10-20 | 11:30 | 15:00 | 3:30 | 23 hours 39 minutes | Got authentication and session figured out between the backend and the frontend | Next step is getting OAuth accounts created in our backend, and merging accounts with the same email
2023-10-21 | 12:00 | 12:32 | 0:32 | 0 hours 11 minutes | Only taking a break to bathroom
2023-10-21 | 13:05 | 15:40 | 2:35 | 2 hours 46 minutes | Got a lot of project API made, added some to auth/account API | Next is adding projects to users, then getting the frontend "register -> login -> create project -> open project" flow
2023-10-21 | 17:05 | 19:05 | 2:00 | 4 hours 46 minutes | Got the register frontend wired to backend alongsied making the security code for the non auth apis, a new project endpoint, and some more account and project endpoints | Next is the dashboard/account page